sukuk.tawf.finance

Technical Roadmap & Execution Plan

HASAN.VC Accelerator Ready — March 2026

"We Tokenize the Warung Economy." Community Green Sukuk for graduating Indonesian warungs. Soulbound NFT bond receipts. USD 10 minimum. No secondary market. Ever.

| Item | Detail |
| --- | --- |
| Product | sukuk.tawf.finance — Warung Economy Sukuk Platform |
| Legal model | tawf.finance = tech vendor (PT Indonesia). Sekuritas partner = licensed bond issuer. |
| Chain | Base (primary) — EVM, Coinbase-backed, gasless via Paymaster |
| Stablecoin | USDC (investment) + IDRX (Indonesia IDR on-chain) + PAXG (gold savings) |
| Target pilot | 3 graduating warungs supplying Indomaret or Alfamart. IDR 10–500 juta invoices. |
| HASAN.VC ask | Up to US$60,000 pre-seed — smart contracts + audit + Sekuritas MOU legal + pilot |
| Document date | March 2026 |

CONFIDENTIAL — FOR INTERNAL AND INVESTOR USE ONLY

# 1. HASAN.VC Alignment — Why This Is Their Thesis

HASAN.VC backs 'Camel Startups' — resilient, sustainable, values-aligned growth. They invest in early-stage halal/ethical tech targeting Southeast Asia. They are powered by Ethis Group, co-founded by Ronald Wijaya (Ethis Indonesia) — who is already in Tawf's direct contact network. This is the highest-probability early funding path for tawf.finance.

| HASAN.VC Investment Criterion | How tawf.finance Scores | Evidence |
| --- | --- | --- |
| Halal & ethical business model | ✅ Perfect | No riba (fixed yield from real invoices). No gharar (individual NFT per invoice, full transparency). No maysir (no secondary market, ever). Sharia structure verified by ABSI. |
| Tech-enabled company | ✅ Perfect | Full smart contract stack on Base. ZK identity via TID. Soulbound ERC-1155 bond receipts. IDRX on-chain settlement. Novel blockchain application. |
| SEA market focus — Indonesia | ✅ Perfect | 64M Indonesian MSMEs. 4,500+ BMT cooperatives. tawf.finance serves the warung economy — the most Indonesian-native use case possible. |
| Impact on humanity | ✅ Strong | Warungs currently resort to pinjol illegal at 300–700% APR. tawf.finance gives them access to global capital at 8–18% annualized halal yield. Direct maslaha. |
| Strong founder-market fit | ✅ Strong | Tawf team: Islamic finance + blockchain + Indonesian market expertise. Direct connections to ABSI (Jodhi), AFSI (Ronald), HAQQ, Mosqify, kripto.ui. |
| Camel startup — resilient, not unicorn | ✅ Perfect | 30–90 day bond cycles = cashflow from day one. Revenue from Sekuritas SaaS licensing + per-deal minting fee. No speculative token. No secondary market. Sustainable by design. |
| Pre-seed stage (<$250K raised) | ✅ Perfect | Pre-product, pre-launch, pre-seed. Exactly HASAN.VC's profile. Under their US$60K funding ceiling for first investment. |
| Ronald Wijaya connection (Ethis co-founder) | ✅ Warm intro available | Ronald is Ethis Indonesia co-founder. HASAN.VC is powered by Ethis. Ronald knows Umar Munshi and Mohd Akhtaar. One message = front of the queue. |

## 1.1 What HASAN.VC Gets From Tawf

| Benefit to HASAN.VC | Detail |
| --- | --- |
| Portfolio differentiation | tawf.finance is the only Islamic Web3 RWA sukuk platform in their portfolio. Differentiated from other halal fintech plays (Takadao is insurance; tawf is capital markets). |
| Indonesia market depth | 60M Muslim partner database access + SUMU/Muhammadiyah warung network = unparalleled halal MSME distribution. No other HASAN portfolio company has this. |
| Blockchain credibility | First on-chain sukuk for Indonesian warungs. HAQQ ecosystem alignment. Tawf puts HASAN.VC on the map in Islamic Web3. |
| Camel economics | 30–90 day cash cycles. Revenue from Sekuritas SaaS + per-deal fees. Profitable at 50 deals/year. Not burning capital waiting for scale. |
| Investor story | Demo Day: 'We funded the technology that lets a global investor put $10 into a warung in East Java and get paid back in 30 days.' That is a story investors remember. |

# 2. Product — What We're Building

sukuk.tawf.finance is a three-portal platform: Investor Portal (global retail, from USD 10), BMT Originator Portal (cooperative underwriting), and Sekuritas Admin Portal (regulated bond issuance). Three portals, one product, one smart contract stack.

## 2.1 How It Works — End-to-End

| Step | Actor | Action | On-Chain Event |
| --- | --- | --- | --- |
| 1 | Warung/MSME | Submits verified invoice from anchor buyer (Indomaret/Alfamart/distributor) + NIB + NPWP + 2 prior fulfilled orders | Off-chain — document hash stored to IPFS |
| 2 | BMT Originator | Underwrites warung using cooperative relationship data. Approves via BMTGateway.sol. | DealRegistry.sol: status = BMT_APPROVED |
| 3 | Sekuritas Partner | Reviews deal. Issues legal bond document. Signs EIP-712 confirmation via SekuritasOracle.sol. | SekuritasOracle.sol: 48h timelock begins |
| 4 | Sekuritas Oracle | 48h safety window passes. Status auto-transitions to MINTABLE. | DealRegistry.sol: status = SEKURITAS_CONFIRMED |
| 5 | Investor (global) | Connects existing wallet + TID verification. Purchases bond receipt NFT from USD 10. | BondReceiptNFT.sol: ERC-1155 soulbound minted |
| 6 | Warung/MSME | Receives working capital. Fulfills order to anchor buyer. Anchor buyer pays. | Off-chain — real commercial transaction |
| 7 | Sekuritas → Vault | Confirms repayment via SekuritasOracle.sol. RedemptionVault.sol distributes. | RedemptionVault.sol: yield distributed pro-rata; NFT burned |
| 8 | Investor | Receives principal + yield to existing wallet. Impact certificate issued to TID. | BondReceiptNFT.sol: burned; TIDHistory: impact logged |

## 2.2 Smart Contract Stack

| Contract | Function | Priority |
| --- | --- | --- |
| DealRegistry.sol | Central on-chain registry of all sukuk deals. Invoice hash, anchor buyer, yield, maturity, BMT originator, status machine. | P0 — build first |
| SekuritasOracle.sol | EIP-712 multisig confirmation from Sekuritas → on-chain. 48h timelock. Resolves the legal-to-blockchain bridge without centralized admin key. | P0 — build first |
| BondReceiptNFT.sol | ERC-1155 soulbound bond receipt. Mints on investor purchase. Non-transferable. Burns on redemption. States: Minted → Active → Matured → Redeemed. | P0 — build first |
| RedemptionVault.sol | Receives repayment signal from Sekuritas oracle. Distributes principal + yield pro-rata to NFT holders. Triggers burn. | P0 — build first |
| BMTGateway.sol | BMT originator access control. Manages which BMTs can submit deals and their revenue share percentage. | P1 — build second |
| SekuritasGateway.sol | Manages authorized Sekuritas EOA addresses. Tawf Labs 3-of-5 multisig controls. Sekuritas cannot unilaterally change their own key. | P1 — build second |
| TawfAudit.sol | Lightweight audit log for Mosqify QRIS webhook integration. Writes SHA-256 hash of donation events to Base. | P2 — Mosqify integration sprint |

## 2.3 Three Portals — sukuk.tawf.finance

| Portal | URL | Users | MVP Features |
| --- | --- | --- | --- |
| Investor Portal | sukuk.tawf.finance/invest | Global retail investors — connect existing wallet + TID | Browse live deals, filter by sector/yield/maturity, buy NFT bond receipts from USD 10, view portfolio, track maturity, claim redemption |
| BMT Originator Portal | sukuk.tawf.finance/originate | BMT cooperative staff — authenticated via BMTGateway.sol | Submit warung deals (IPFS invoice upload, anchor buyer verification), track deal status, view revenue share |
| Sekuritas Admin Portal | sukuk.tawf.finance/sekuritas | Licensed Sekuritas partner staff — authenticated via SekuritasGateway.sol | Review pending deals, sign EIP-712 bond confirmation, confirm repayments, download compliance reports |

# 3. Technical Roadmap — 20 Weeks to HASAN.VC Demo Day

Target state for HASAN.VC Demo Day: sukuk.tawf.finance testnet live end-to-end. One simulated warung deal complete (invoice → NFT → repayment → redemption). Sekuritas MOU signed or in advanced negotiation. ABSI as verification partner MOU signed. SUMU/Jodhi pilot pipeline confirmed (3 warungs identified). TID verification working. Mosqify webhook integration live on one mosque.

## 3.1 Phase 0 — Foundation (Weeks 1–2)

Before writing a single line of smart contract code, three things must exist: the legal structure, the Sekuritas partner, and the development environment. Code without these is a prototype, not a product.

| W1–2 | Phase 0: Foundation IN PROGRESS ▸ PT Indonesia entity incorporated (or existing entity confirmed as tawf.finance vehicle) ▸ Sekuritas outreach ACTIVE: Ina Sekuritas Singapore (Plan A) + Trimegah Sekuritas (Plan B) — simultaneous ▸ ABSI kopdar with Mas Jodhi — MOU framework discussed ▸ Development environment: Base Sepolia testnet, Hardhat/Foundry setup, Solidity 0.8.x ▸ HASAN.VC WhatsApp community: active engagement started. Ronald WA conversation initiated. ▸ Architecture decision log confirmed: Noir (ZK), Base canonical, Across bridge, IDRX stablecoin, SekuritasOracle multisig ▸ GitHub monorepo created: /contracts, /frontend-investor, /frontend-bmt, /frontend-sekuritas, /scripts ▸ Also add kurban sukuk(3 month fixed staking) that offers investors to buy kurban farms sukuk |
| --- | --- |

## 3.2 Phase 1 — Core Smart Contracts (Weeks 3–6)

Build and test the four P0 contracts on Base Sepolia testnet. These are the minimum viable on-chain stack — without them nothing works. Everything else waits for these to be solid.

| W3 | DealRegistry.sol + SekuritasOracle.sol W3 TARGET ▸ DealRegistry.sol: full state machine (SUBMITTED → BMT_APPROVED → SEKURITAS_CONFIRMED → MINTING → ACTIVE → MATURED → COMPLETE/DEFAULTED) ▸ SekuritasOracle.sol: EIP-712 structured message verification, 48h timelock, multi-sig pattern ▸ Unit tests: 100% coverage on state transitions. Fuzz tests on oracle signature verification. ▸ Deploy to Base Sepolia. Document ABI + event signatures. |
| --- | --- |

| W4 | BondReceiptNFT.sol — Soulbound ERC-1155 W4 TARGET ▸ ERC-1155 soulbound implementation: override all transfer functions to revert ▸ NFT states: Minted → Active → Matured → Redeemed (burned) / Defaulted ▸ Metadata: on-chain (bondId, supplierName, anchorBuyer, invoiceAmount, yield, maturity, BMT, status) ▸ mint() callable only after SekuritasOracle confirms MINTABLE ▸ burn() callable only by RedemptionVault.sol on successful redemption ▸ Unit tests: transfer revert tests, state transition tests, metadata integrity tests |
| --- | --- |

| W5 | RedemptionVault.sol + Integration Tests W5 TARGET ▸ RedemptionVault.sol: receives repayment from SekuritasOracle confirmRepayment(). Pro-rata distribution to NFT holders. Triggers burn. ▸ End-to-end integration test on Base Sepolia: deal created → oracle confirms → NFT minted → repayment confirmed → yield distributed → NFT burned ▸ Gas optimization pass: target <200K gas per NFT mint, <150K per redemption ▸ Security review: reentrancy guards, access control, oracle manipulation prevention |
| --- | --- |

| W6 | BMTGateway.sol + SekuritasGateway.sol + Testnet Hardening W6 TARGET ▸ BMTGateway.sol: BMT registration, suspension, revenue share config ▸ SekuritasGateway.sol: Sekuritas EOA management via 3-of-5 multisig ▸ Full testnet scenario: 3 mock deals in parallel, different states simultaneously ▸ Chaos testing: oracle timeout, partial repayment, defaulted deal ▸ ITIDRegistry.sol + ITIDVerifier.sol interface integration (mock TID for testnet) ▸ Code freeze: no new features added to core contracts after W6 |
| --- | --- |

## 3.3 Phase 2 — Frontend Portals (Weeks 7–10)

Three portals, built in parallel by splitting frontend responsibilities. Shared: Next.js 14, Wagmi v2, Viem, Tailwind CSS, deployed on Vercel.

| W7–8 | Investor Portal — sukuk.tawf.finance/invest W7–8 TARGET ▸ Connect existing wallet (MetaMask, Coinbase Wallet, WalletConnect) — no new wallet created ▸ TID verification: ZK proof via hosted Noir server (mock TID for testnet) ▸ Deal browser: filter by sector, yield range, maturity, anchor buyer ▸ Deal detail page: invoice metadata, anchor buyer, BMT originator, yield, maturity, full audit trail ▸ Buy flow: USDC → BondReceiptNFT.sol mint. Gasless via Base Paymaster. ▸ Portfolio view: active NFTs, maturity countdown, claim button when matured ▸ Mobile-responsive: target Rp 1.5–3 juta Android devices (SEA median) |
| --- | --- |

| W9 | BMT Originator Portal — sukuk.tawf.finance/originate W9 TARGET ▸ BMT staff login via wallet + BMTGateway.sol authentication ▸ Deal submission form: warung details, IPFS invoice upload, anchor buyer selection ▸ Deal status tracker: see all submitted deals and their current state ▸ Revenue share dashboard: track accumulated revenue per deal ▸ Warung pipeline view: qualified warungs in pipeline, rejection reasons |
| --- | --- |

| W10 | Sekuritas Admin Portal — sukuk.tawf.finance/sekuritas W10 TARGET ▸ Sekuritas staff login via SekuritasGateway.sol authenticated wallet ▸ Pending deals queue: review invoice, warung details, BMT underwriting ▸ Approve flow: sign EIP-712 message → SekuritasOracle.sol confirmIssuance() ▸ Repayment flow: confirm repayment → SekuritasOracle.sol confirmRepayment() ▸ Compliance export: downloadable deal reports for regulatory filing ▸ Reject flow: reason logged on-chain, BMT notified |
| --- | --- |

## 3.4 Phase 3 — TID Integration + Security (Weeks 11–13)

Swap out mock TID for real TIDRegistry.sol interfaces. Add ZK proof generation. Complete security review. This is the phase that makes the testnet 'real.'

| W11–12 | Real TID Integration + ZK Proving W11–12 TARGET ▸ Deploy ITIDRegistry.sol + ITIDVerifier.sol pointing to Tawf Foundation's TIDRegistry on Base Sepolia ▸ Hosted Noir proving server: deploy on Vercel edge (Jakarta PoP for SEA latency) ▸ Investor portal: real ZK proof generation for TID verification. Cache proofs 24h. ▸ Test on real Android devices (Rp 2 juta range) — prove <3s proof generation ▸ TID tier gating: Standard tier minimum to invest. Trusted tier for >$500 investment. ▸ IDRX integration: IDRX.co API for IDR-denominated display. All amounts shown in IDR + USD. |
| --- | --- |

| W13 | Security Review + Testnet Hardening W13 TARGET ▸ Internal security audit: access control, reentrancy, oracle manipulation, gas griefing ▸ External review: engage at least one external security researcher via Immunefi or Code4rena ▸ Penetration test: API endpoints, IPFS upload validation, wallet signature replay attacks ▸ Multi-sig configuration: Tawf Labs 3-of-5 multisig deployed on Base Sepolia ▸ Formal test: run a complete simulated deal from warung submission to investor redemption — publicly document results ▸ Bug bounty: Immunefi listing goes live (even pre-mainnet — shows maturity) |
| --- | --- |

## 3.5 Phase 4 — Pilot Preparation + Mosqify Integration (Weeks 14–16)

First real-world connections. Sekuritas MOU signed (or in final negotiation). SUMU warung pipeline confirmed. Mosqify webhook integration shipped.

| W14 | Sekuritas MOU + Legal Structure W14 TARGET ▸ Sekuritas MOU target: signed (Ina Sekuritas or Trimegah — whichever moves first) ▸ Legal review: OJK-registered lawyer reviews sukuk structure and Sekuritas agreement ▸ Profit-sharing terms defined: Sekuritas fee %, Tawf SaaS fee %, BMT revenue share %, investor yield ▸ Compliance report template: Sekuritas Admin Portal export format approved by partner ▸ If MOU not yet signed: term sheet agreed + legal in progress. Document signed letter of intent. |
| --- | --- |

| W15 | SUMU Pilot Pipeline — 3 Warungs Identified W15 TARGET ▸ Via Jodhi (SUMU Blockchain Coordinator): 3 qualifying warungs identified in Java ▸ Qualification checklist: NIB + NPWP verified, 2 prior anchor buyer orders confirmed, invoice in IDR 50–200 juta range, anchor buyer is Indomaret/Alfamart/verified distributor ▸ Warung KYC: ZK-friendly data collection (no PII stored on Tawf servers) ▸ Deal structure per warung: 30-day maturity, fixed yield 12–15% annualized, minimum investment $10 USDC ▸ Pilot terms agreed with SUMU: SUMU as BMT originator, revenue share 30% of Tawf's minting fee |
| --- | --- |

| W16 | Mosqify Webhook Integration — TawfAudit.sol W16 TARGET ▸ Product demo with Fajar: understand Mosqify payment webhook format and event structure ▸ TawfAudit.sol deployed on Base Sepolia: lightweight audit log (amount hash, fund type, mosque ID, timestamp) ▸ Tawf webhook listener: Node.js service that receives Mosqify payment webhook → writes to TawfAudit.sol ▸ Donor verification UI: basescan link generated per donation — 'Your Rp 50,000 is permanently recorded on-chain' ▸ Test with Fajar: one real mosque DKM demo. If successful → propose YPI Al-Azhar flagship mosque pilot. ▸ This is Option A (webhook snippet). Option B (QRIS → IDRX) planned for post-Demo Day. |
| --- | --- |

## 3.6 Phase 5 — HASAN.VC Application + Demo Day Prep (Weeks 17–20)

The product is built. The pilot is live. Now: tell the story. Apply to HASAN.VC Cohort 004. Prepare Demo Day materials. Run the first real warung deal on testnet with SUMU partners observing.

| W17 | HASAN.VC Application Submission W17 TARGET ▸ Application submitted to HASAN.VC Cohort 004 (apply at hasan.vc when open) ▸ Ronald Wijaya intro to Umar Munshi / Mohd Akhtaar — warm signal before application ▸ Application content: problem (warung financing gap), solution (community Green Sukuk), traction (ABSI MOU, SUMU pipeline, Mosqify integration), ask (US$60,000 for mainnet audit + pilot) ▸ Supporting materials: testnet demo video, smart contract repo link (public), ABSI MOU copy ▸ Equity offer: prepared but not disclosed in application — to be discussed in interview |
| --- | --- |

| W18 | Full Testnet Demo — End-to-End W18 TARGET ▸ Run a complete simulated warung deal on Base Sepolia with SUMU observers watching live ▸ Invoice submitted → BMT approved → Sekuritas confirmed (mock) → NFT minted → investor buys → 30 days simulated → repayment → yield distributed → NFT burned ▸ Record the entire flow as a screen recording. This IS the Demo Day demo. ▸ Publish deal analytics: gas used per step, proof generation time, end-to-end time ▸ Invite Jodhi and one SUMU warung owner to observe testnet demo — their reaction is the testimonial |
| --- | --- |

| W19–20 | HASAN.VC Demo Day Preparation W19–20 TARGET ▸ 3-minute Demo Day pitch: Problem → Market size → Product demo → Traction → Team → Ask ▸ Pitch deck: 10 slides. Lead with warung impact story, not blockchain architecture. ▸ Live demo: sukuk.tawf.finance/invest on testnet. Buy a $10 mock bond receipt NFT on stage. ▸ Traction slide: ABSI MOU signed, SUMU 3 warungs in pipeline, Mosqify integration live, Mas Jodhi endorsement, Ronald Wijaya connection confirmed ▸ Financial model: 3 scenarios (conservative/base/optimistic) for 24 months post-investment ▸ Legal structure: PT Indonesia confirmed, Sekuritas MOU status, OJK sandbox application timeline ▸ Practice: 5 pitch rehearsals. Time to <3 minutes. Demo must work on stage without errors. |
| --- | --- |

# 4. Milestones Summary — HASAN.VC Evaluation Checkpoints

HASAN.VC evaluates startups on founder strength, business potential, and impact. These milestones are designed to show verifiable, on-chain-provable progress — not promises. Each one can be independently verified by any evaluator.

| Milestone | Target Week | Verifiable On-Chain? | HASAN.VC Signal |
| --- | --- | --- | --- |
| P0 contracts deployed on Base Sepolia (DealRegistry, SekuritasOracle, BondReceiptNFT, RedemptionVault) | W5 | ✅ Yes — Basescan | Technical execution ability confirmed |
| ABSI MOU signed — Mas Jodhi as Sharia Verification Partner | W6 | ✅ Document + public announcement | Institutional legitimacy — ABSI endorses the product |
| Investor portal live on testnet | W8 | ✅ URL accessible | Product exists, not just whitepaper |
| SUMU 3 warungs identified and qualified | W15 | ✅ Deal submissions visible on testnet DealRegistry | Real market traction — warungs want this |
| Sekuritas MOU signed (or term sheet) | W14 | ✅ Document | Legal viability confirmed — regulated partner committed |
| Mosqify webhook integration live (TawfAudit.sol) | W16 | ✅ Basescan transaction hash from real mosque | B2B expansion pathway proven. Al-Azhar network access. |
| Ronald Wijaya endorsement confirmed | W2 | ✅ Public or private reference letter | Ethis Group co-founder = HASAN.VC warm intro |
| Full testnet demo recorded and published | W18 | ✅ Video + Basescan links | Product works end-to-end. Demo Day ready. |
| HASAN.VC application submitted | W17 | ✅ Confirmation email | In the funnel |
| First real warung deal on mainnet (post-HASAN.VC investment) | Post-Demo Day | ✅ Basescan mainnet | Use of funds: mainnet launch is the first funded deliverable |

# 5. Use of HASAN.VC Funds — US$60,000

All fund allocation is traceable on-chain where applicable. Smart contract deployment costs, audit fees, and legal fees are real, fixed, non-negotiable costs to bring sukuk.tawf.finance to mainnet. No salaries drawn from HASAN.VC pre-seed — founders are working on equity until post-Demo Day.

| Allocation | Amount (USD) | % of Total | What It Buys | When |
| --- | --- | --- | --- | --- |
| Smart contract external security review | $10,000 | 17% | One independent security researcher via Immunefi/Code4rena for core P0 contracts before mainnet. Not a full Certora audit — that comes at Series A. | W13 (pre-Demo Day) |
| Sekuritas MOU legal fees | $5,000 | 8% | OJK-familiar lawyer to draft and review the Sekuritas technology service agreement and sukuk structuring framework. | W14 |
| PT Indonesia incorporation (if needed) | $1,200 | 2% | Legal entity for tawf.finance if not yet incorporated. Notary + Kemenkumham fees. | W1 |
| Frontend deployment infra (Vercel Pro + Upstash) | $1,800 | 3% | 12 months Vercel Pro ($20/mo) + Upstash Redis ($50/mo) + domain + SSL. All three portals. | Immediate |
| Base Sepolia → Mainnet migration costs | $2,000 | 3% | Gas for mainnet contract deployment (Foundry scripts). Base Paymaster setup. IPFS storage (web3.storage paid tier). | Post-Demo Day |
| ABSI MOU legal drafting | $2,000 | 3% | Lawyer to draft the Tawf Foundation ↔ ABSI collaboration MOU. Clean legal instrument. | W6 |
| Pilot warung onboarding (travel + integration) | $5,000 | 8% | Onboarding 3 SUMU warungs: travel to Java (if needed), document collection assistance, BMT integration support, warung owner training. | W15 |
| Mosqify integration development | $3,000 | 5% | TawfAudit.sol development + webhook listener service + Fajar integration support. | W16 |
| Working capital reserve | $30,000 | 50% | Runway buffer: 6 months of operating costs (infra, legal, miscellaneous) while building toward Series A. Not drawn unless needed. | On-demand |

| Total | $60,000 | 100% | Mainnet-ready sukuk.tawf.finance + first warung pilot + 6-month runway |  |
| --- | --- | --- | --- | --- |

# 6. Technology Stack — Decided & Locked

All major architecture decisions are formally closed. No rearchitecting during the 20-week sprint. Changes require a formal Architecture Review with CTO + two engineers.

| Layer | Technology | Decision | Why |
| --- | --- | --- | --- |
| Smart contracts | Solidity 0.8.x + Foundry | LOCKED | Industry standard. Foundry for fast compilation and fuzz testing. Hardhat as backup for complex scripts. |
| Primary chain | Base (Coinbase L2, EVM) | LOCKED | Base App distribution. Coinbase Wallet native. Base Paymaster gasless. x402 native. $50K Base Ecosystem Fund pathway. |
| ZK framework | Noir (Aztec) + Barretenberg prover | LOCKED | 3–5x faster than SnarkJS. UltraPlonk smaller proofs = cheaper verification. Better developer ergonomics for 2026 hiring. |
| TIDRegistry | Base (canonical chain) | LOCKED | Single source of truth for TID. Celo is product chain for secondary deployment. No split registry. |
| PAXG bridge | Across Protocol | LOCKED | 2 min vs 7 days (official bridge). Competitive fee. Established security. |
| Sekuritas oracle | SekuritasOracle.sol — EIP-712 + 48h timelock | LOCKED | Neither party (Tawf nor Sekuritas) can act unilaterally. Multisig + timelock = minimum viable trustless design. |
| IDR stablecoin | IDRX (idrx.co) — on Base | LOCKED | 1:1 IDR. BAPPEBTI-registered. CertiK audited. Base-native. Jesse Pollak (Coinbase/Base) endorsed. Only IDR stablecoin on Base. |
| USDC (investment) | USDC on Base (Circle) | LOCKED | Largest regulated stablecoin. Native on Base. No algorithmic stablecoin ever. |
| Frontend framework | Next.js 14 (App Router) + TypeScript | LOCKED | Full-stack SSR. API routes in one deployment. MiniKit/OnchainKit compatible. |
| Frontend chain | Wagmi v2 + Viem | LOCKED | Type-safe Ethereum interactions. Best-in-class for Base/EVM. |
| Wallet connection | Coinbase Smart Wallet via MiniKit | LOCKED | Passkey (FaceID/fingerprint) onboarding. No seed phrase. No extension. Gasless via Paymaster. |
| Mobile ZK proving | Hosted Noir server (Vercel edge) | LOCKED | Default for SEA mobile (Rp 2 juta Android median). Browser proving opt-in for privacy-maximalists. |
| Storage (docs) | IPFS via web3.storage | LOCKED | Decentralised. Hash written on-chain. No Tawf server stores invoice documents. |
| Monitoring | Tenderly + Chainalysis | LOCKED | Real-time bridge + contract anomaly detection. Auto-pause on anomalous flow. |
| Secondary chain | HAQQ / Ethiq L2 (post-HASAN.VC) | PLANNED | Same Solidity code redeploys to HAQQ/Ethiq. $40M HAQQ Ecosystem Fund target. HAQQ's MUI fatwa endorsement. |

# 7. Risk Log — What Could Delay Demo Day

| Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Sekuritas MOU delays — partner regulatory review takes >8 weeks | HIGH | Critical — blocks mainnet launch (not Demo Day) | Three plans in parallel (Ina, Trimegah, Mandiri). Testnet demo does NOT require real Sekuritas MOU — mock oracle covers Demo Day. MOU is for mainnet, not Demo Day. | CEO |
| Smart contract bug found in W13 security review | MEDIUM | High — delays W14+ if critical | Code freeze at W6. Security review W13 = 7 weeks of review buffer before Demo Day W19. Non-critical bugs documented but do not block testnet demo. | CTO |
| Fajar unavailable / Mosqify integration delayed | LOW | Low — Mosqify is a nice-to-have for Demo Day, not critical path | TawfAudit.sol is a 1-week build. If Fajar is slow, build against mock webhook. Ship the contract regardless. | CTO |
| HASAN.VC Cohort 004 applications close before W17 | MEDIUM | High — miss the cohort | Monitor hasan.vc weekly. If applications open earlier, submit with W10 progress (portals live) rather than waiting for W17. Ronald intro can hold the slot. | CEO |
| SUMU warung qualification takes longer than 2 weeks | MEDIUM | Medium — Demo Day traction slide weakened | Direct warung sourcing (Fajar Expo, Instagram UMKM) runs in parallel. If SUMU slow: show 1 warung qualified, not 3. Still a traction signal. | COO |
| Base Paymaster API changes or pricing | LOW | Low — fallback is user pays gas (~$0.01 on Base) | Paymaster is a UX enhancement, not a core requirement. If it breaks, users pay nominal gas. Demo Day demo uses a funded wallet anyway. | CTO |

# 8. Team Responsibilities — 20-Week Sprint

| Role | Person | Responsibilities During Sprint | Weeks Active |
| --- | --- | --- | --- |
| CEO / Founder | Founder | Sekuritas MOU (all three plans in parallel). ABSI kopdar → MOU. Ronald WA → HASAN.VC intro. SUMU warung pipeline. HASAN.VC application. Demo Day pitch. | All — 20 weeks |
| CTO | CTO | Smart contract development (P0 → P2). Security review coordination. ZK proving server deployment. Frontend architecture leadership. Testnet demo recording. | W3–20 — all sprint phases |
| COO | COO | SUMU warung qualification and onboarding. BMT originator portal requirements. Pilot logistics (travel, document collection, training). OJK monitoring. | W14–20 — pilot phase |
| Co-founder — Research (cofounder) | Cofounder | Research tasks R1–R13 from Ontology Report. HASAN.VC application content. Pitch deck narrative. Financial model. Market data for Demo Day slides. | W1–20 — parallel to build |
| Co-founder — DBC + UI (Dicky) | Dicky Bayu | kripto.ui developer recruitment pipeline (NOW). Dubai Blockchain Center relationship prep. UI academic partnership proposal. | W1–4 (kripto.ui NOW); W17–20 (UAE prep) |
| External — Sharia Review | Ustad Devin (advisory) | TAWF Framework review of murabaha, zakat, sukuk structures. Written sharia advisory letter for HASAN.VC application. | W8–10 — targeted advisory |

# 9. Demo Day — What Tawf Shows on Stage

Three minutes. One live demo. One compelling story. No slides about blockchain. The blockchain is invisible. The warung is the story.

## 9.1 The 3-Minute Pitch Structure

| Minute | Section | Content | Key Message |
| --- | --- | --- | --- |
| 0:00–0:30 | The Problem | 'A warung in East Java has a verified Indomaret order for Rp 200 juta. She needs working capital now. Her bank says no — no credit history. Her only option is pinjol at 400% APR. There are 64 million of her in Indonesia.' | The problem is real, urgent, and massive |
| 0:30–1:15 | The Product (live demo) | Open sukuk.tawf.finance/invest on screen. Show a live testnet deal. Connect a wallet. Buy a $10 mock bond receipt NFT. Show the soulbound NFT in the wallet. Show the countdown to repayment. | The product works. It's live. You can use it right now. |
| 1:15–1:45 | The Traction | 'We have: ABSI signed as sharia verification partner. Mas Jodhi from SUMU Blockchain with 3 warungs in pipeline ready for first pilot. Mosqify integration live — every donation to Masjid Al-Azhar is now on-chain. Ronald Wijaya from Ethis Indonesia advising.' | Real institutional relationships. Real distribution. |
| 1:45–2:15 | The Market | '$88B RWA tokenization potential in Indonesia. 64M MSMEs. 4,500+ BMT cooperatives. USD 10 minimum — accessible to any investor globally. 8–18% annualised yield from real invoices, not algorithms.' | The market is enormous and the timing is now |
| 2:15–2:45 | The Ask | 'We are raising US$60,000 pre-seed via HASAN.VC to complete our security audit, sign our first Sekuritas MOU, and run our first live warung deal on mainnet. We are SEA-native, sharia-compliant, and we are building for the next 20 years, not the next 20 months.' | Camel startup. Long game. Right amount. |
| 2:45–3:00 | The Close | 'The warung doesn't need a bank. She needs infrastructure. That's what we built. tawf.finance.' | Memorable. Simple. Repeatable. |

## 9.2 Demo Day Success Criteria

| Criteria | Target | Status at Demo Day |
| --- | --- | --- |
| sukuk.tawf.finance testnet: live and accessible | 100% uptime during Demo Day | ✅ Deployed W8, hardened W13 |
| Live NFT mint on stage | Buy $10 USDC mock bond receipt NFT in <60 seconds | ✅ Gasless via Base Paymaster, no errors |
| ABSI MOU: signed | Signed MOU document available to show | Target W6 |
| Sekuritas: MOU or term sheet | At minimum a signed term sheet with one Sekuritas partner | Target W14 |
| SUMU warung pipeline: 3 qualified | 3 named warungs with verified invoices in DealRegistry on testnet | Target W15 |
| Mosqify integration: live | One real mosque transaction visible on Basescan | Target W16 |
| Ronald Wijaya: confirmed reference | Email or message from Ronald confirming Tawf for HASAN.VC investors | Target W2 |
| Sharia advisory letter: from Ustad Devin | Written letter reviewing and endorsing Tawf's product structure | Target W10 |

sukuk.tawf.finance

We tokenize the warung economy.

Ethical by Principle. Sharia by Design.

sukuk.tawf.finance  |  tawf.finance  |  tawf.foundation  |  contact@tawf.finance